| Risk 1 |  |  |  | There is a risk of worsening health in the population of Wales, particularly among vulnerable populations Caused by the cumulative effects of current socio-economic, environmental and wider public health challenges and failure to influence the embedding of health in all policies Resulting in a widening gap in healthy life expectancy |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Owner’s Overview Assessment Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prior to the pandemic the gap in healthy life expectancy between the most and least deprived populations of Wales was widening. The consequences of the pandemic in terms of access to preventative and healthcare services and the impact on mental and emotional well-being is likely to have exacerbated this. Together with the health impacts of the ongoing Cost of Living Crisis there is a high risk that the health of the population will worsen, particularly for vulnerable populations. This is likely to increase the gap in healthy life expectancy among our vulnerable, more deprived populations compared to more affluent populations in Wales. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sponsor and Assurance Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Executive Sponsor |  |  |  |  |  | Angela Jones, Exec Director of Health and Wellbeing Contributors: Sumina Azam, Director of Policy and International Health / WHOCC Meng Khaw, National Director Health Protection and Screening Services Huw George, Deputy Chief Executive and Exec Director of Operations and Finance |  |  |  |  |  |  |  |  |  |  |  |
| Assurance Group |  |  |  |  |  | Quality, Safety and Improvement Committee |  |  |  |  |  |  |  |  |  |  |  |
| Inherent Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | 11/05/23 |  |  |  |  | Likelihood: |  |  | 5 | Impact: | 5 | Score: |  | 25 |  |  |
| Risk Score |  |  |  |  |  |  |  |  |  |  | Risk Decision |  |  | Delivery Confidence Assessment |  |  |  |
| Current Risk |  |  |  |  | Target Risk |  |  |  |  |  | Treat |  |  | AMBER |  |  |  |
| Likelihood | Impact |  | 20 |  | Likelihood |  |  | Impact | 9 |  |  |  |  |  |  |  |  |
| 4 | 5 |  |  |  | 3 |  |  | 3 |  |  |  |  |  |  |  |  |  |

|  | EXISTING CONTROLS |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 1.1 | Providing leadership for health in all policies through maximising opportunities through Welsh legislation including Public Health Act (Health Impact Assessment), the Well-being of Future Generations Act and the Socio-economic Duty | Director of Policy and International Health | Performance monitoring of IMTP delivery through Leadership Team | X | X | X |  |  |
| SR 1.2 | Implementing the WHO Collaborating Centre on Investment for Health and Wellbeing workplan, such as establishing a health equity solutions platform, to identify causes and solutions for tackling the health gap in Wales | Director of Policy and International Health | KRIC minutes Annual return to WHO of delivery of workplan Performance monitoring of IMTP delivery through Leadership Team | X | X | X | X |  |
| SR 1.3 | Identifying and translating international learning on tackling health inequity, for example through International Horizon Scanning and strengthened international partnerships with WHO, IANPHI, EuroHealthNet | Director of Policy and International Health, National Director of Health Protection and Screening Services | Board minutes KRIC minutes Performance monitoring of IMTP delivery through Leadership Team | X | X | X | X | X |
| SR 1.4 | Influencing and informing policy to reduce health inequity through research and advocacy on the wider determinants of health such as fair work, housing, spatial planning | National Director of Health and Well-being, Director of Policy and International Health | Performance monitoring of IMTP delivery through Leadership Team | X | X | X |  |  |
| SR 1.5 | Tackling the public health effects of climate change agreed as an organisational strategic priority | Deputy CEO/Director of Ops and Finance, National Director of Health Protection and Screening Services, Director of Policy and International Health | Climate Change Programme Board minutes |  | X | X |  |  |
| SR 1.6 | Systems leadership and partial delivery of improvement programmes for primary and secondary prevention | National Director of Health and Well-being National Director of Health Protection and Screening Services | Performance monitoring of IMTP delivery through Leadership Team |  | X | X |  |  |

| Action plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 1.1 | No agreed organisational narrative of tackling health inequalities |  | Workshop planned with Executive Team to explore organisational understanding and agree next steps | National Director of Health and Well-being, Director of Policy and International Health | June 2023 | July 2023 update - Strategic Executive meeting held 27/6/23. Task and Finish Group to be set up to progress delivery. |
| AP 1.2 | A comprehensive three year IMTP with action based on proportionate universalism and targets, where appropriate |  | Development and monitoring of a comprehensive three year IMTP with action based on proportionate universalism and targets, where appropriate | All Execs | March 2024 |  |
|  |  |  | Organisational Inclusion Health Group to develop an action plan, informed by behavioural insights, to guide all programmes delivered by Public Health Wales | National Director of Screening and Health Protection Services and Medical Director | March 2024 |  |
|  |  |  | Prioritisation based on evidence of effectiveness, Return on Investment and Social Return on Investment | National Director of Health and Well-being/ National Director of Policy and International Health | March 2024 |  |
| AP 1.3 | A Framework for Healthcare Public Health to influence the NHS to shift systematically towards prevention and Early Intervention |  | Develop a framework to influence and facilitate the NHS to shift systematically towards prevention and early intervention | National Director of Health and Well-being | December 2023 |  |
| AP 1.4 | Systematic collection of equalities data across all protected characteristics for the NHS in Wales to enable monitoring of public health |  | Work with Welsh Government and DHCW to prioritise and implement better collection of equalities data | Director for Data, Knowledge and Research | April 2024 |  |
| AP 1.5 | Co-ordination of activity to address the needs of underserved populations |  | Establish an inclusion health programme in PHW | National Director of Health Protection and Screening Services | December 2023 | Progress is challenged by support of DDHPSS to Public Inquiry Board. Scoping Report deferred to September. Link to cross organisational work on Inequality in Health? |
| AP 1.6 | Effective monitoring and evaluation of health and healthcare improvement programmes |  | Develop data products to inform monitoring, evaluation and optimisation of programmes | National Director of Health and Well-being / National Director of Data, Knowledge and Research | December 2023 |  |

| Risk 2 | There is a risk of ineffective system-wide efforts to improve health and wellbeing by organisations across public, private and third sectors. Caused by misaligned system-wide efforts and leadership, and weaknesses in partnership working. Resulting in worsening health outcomes and suboptimal use of limited public resources. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Owner’s Overview Assessment Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| There is a risk that the specialist public health system in Wales will fragment further following the transfer of the Local Public Health Teams to the Health Boards. Work is underway to develop a Memorandum of Understanding with Welsh Government, Public Health Wales, Health Boards and Local Authorities to agree the principles and mechanisms of effective systems and an agreed system population health work plan. There is not yet sufficient strategic agreement to align collective efforts between the third sector and Public Health Wales. Discussion has commenced with WCVA which needs to translate into a meaningful collaboration with an underpinning MOU to reflect the intention of better alignment and partnership working. Cross reference with risk 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sponsor and Assurance Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Executive Sponsor |  |  |  |  |  | Angela Jones, Exec Dir of Health and Wellbeing Contributors: Rhiannon Beaumont-Wood, Exec Dir Quality, Nursing and Allied Health Professionals Huw George, Deputy Chief Executive and Executive Director of Operations and Finance John Boulton, Director for NHS Quality Improvement and Patient Safety |  |  |  |  |  |  |  |  |  |  |  |
| Assurance Group |  |  |  |  |  | Quality, Safety and Improvement Committee |  |  |  |  |  |  |  |  |  |  |  |
| Inherent Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  | 11/05/23 |  |  |  | Likelihood: |  |  | 4 | Impact: | 4 | Score: |  | 16 |  |  |
| Risk Score |  |  |  |  |  |  |  |  |  |  | Risk Decision |  |  | Delivery Confidence Assessment |  |  |  |
| Current Risk |  |  |  |  | Target Risk |  |  |  |  |  | Treat |  |  | AMBER |  |  |  |
| Likelihood |  | Impact |  | 16 | Likelihood |  |  | Impact | 6 |  |  |  |  |  |  |  |  |
| 4 |  | 4 |  |  | 3 |  |  | 2 |  |  |  |  |  |  |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 2.1 | CMO’s Monthly meeting with the Public Health Leadership Group and Directors of Public Protection for Wales | National Director of Health and Well-being | Minutes presented in the Forum |  | X |  |  |  |
| SR 2.2 | Monthly meeting with the Public Health Leadership Group and bi-weekly informal Public Health Wales/DsPH group | National Director of Health and Well-being | Minutes of PHDLG |  | X |  |  |  |
| SR 2.3 | Whole system approach to healthy weight | National Director of Health and Well-being | Performance monitoring of IMTP delivery through Leadership Team | X | X | X |  |  |
| SR 2.4 | System leadership working groups on priority topics and outcomes | National Director of Health and Well-being | Performance monitoring of IMTP delivery through Leadership Team | X | X | X |  |  |
| SR 2.5 | Wider determinants of health and well-being unit leadership for improving systems working in Public Services Boards. | National Director of Health and Well-being | Performance monitoring of IMTP delivery through Leadership Team | X | X | X |  |  |

| Action plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 2.1 | Clear working arrangements with Public Health Wales, WCVA and other identified third sector organisations on shared objectives |  | Agree how PHW will work with WCVA and other identified third sector organisations to collaborate on shared public health objectives. | Rhiannon Beaumont-Wood, Exec Dir Quality, Nursing and Allied Health Professionals | Sept 2023 |  |
|  |  |  | Complete stakeholder mapping exercise to identify strategic partnerships | Rhiannon Beaumont-Wood, Exec Dir Quality, Nursing and Allied Health Professionals | Sept 2023 |  |
|  |  |  | Complete a base line assessment of which current third sector organisations are engaging regularly with Public Health Wales with a view to having a more joined up approach to third sector stakeholder engagement which is captured and can be evidenced to inform better planning and coordination. | Rhiannon Beaumont-Wood, Exec Dir Quality, Nursing and Allied Health Professionals | October 2023 |  |
| AP 2.2 | Agreed system wide approach to maximise the effectiveness of the specialist public health system following the TUPE transfer of LPHTs to Health Boards |  | Development, approval and implementation of MOU2 for the specialist Public Health System in Wales | National Director of Health and Well-being | October 2023 |  |
|  |  |  | Development and approval of a specialist public health system action plan | National Director of Health and Well-being | October 2023 |  |
| AP 2.3 | System leadership skills of the public health workforce and partnerships. |  | Training and support for systems leadership for the specialist PH system, PSBs, and Public Health Wales staff | National Director of Health and Well-being/Director of People and Organisational Development | March 2024 |  |
| AP 2.4 | Monitoring and evaluation of reach, take up and impact of Health and Healthcare Improvement Programmes |  | Development of outcome, improvement and impact measures, including inclusion | National Director of Health and Wellbeing | March 2024 |  |
| AP 2.5 | Strengthening systems leadership and engagement of Public Services Boards in the wider determinants of Health and Well-being |  | Health Foundation funded feasibility study to engage PSBs | National Director of Health and Wellbeing | September 2023 |  |
|  |  |  | Health Foundation bid for 3 year support to strengthen the system with PSBs | National Director of Health and Wellbeing | March 2024 |  |
| AP 2.6 | See action plan for risk 6 |  |  |  |  |  |

| Risk 3 | There is a risk that people in Wales are insufficiently engaged and enabled on action they can take to improve their health and wellbeing. Caused by failure to provide people with sufficient quality information, motivation, choice and access to timely advice and services. Resulting in people feeling they are limited in exercising control over their health and wellbeing and avoidable poor health outcomes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Owner’s Overview Assessment Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Engaging with our population is central to better understanding health needs and empowering people to co-design public health solutions and become partners in their health and well-being. However, with significant impacts on the conditions for health resulting from the pandemic and more recently, the cost of living crisis, empowering our population becomes even more challenging and there is a risk of widening health inequalities unless actions taken involves working with our communities and using a proportionate universalism approach. Actions are underway across organisational programmes, and all organisational strategic priority areas, to understand the views of our population (including young people) around factors that determine their health, and obtain proactive feedback from people we work with and for. Cross reference to Risk 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sponsor and Assurance Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Executive Sponsor |  |  |  |  |  | Sumina Azam, Director of Policy and International Health / WHOCC Contributors: Angela Jones, Exec Director Health and Wellbeing Meng Khaw, National Director, Health Protection and Screening Services Huw George, Deputy Chief Executive and Exec Director of Operations and Finance Rhiannon Beaumont-Wood, Exec Director of Quality, Nursing and Allied Health Professionals |  |  |  |  |  |  |  |  |  |  |  |
| Assurance Group |  |  |  |  |  | Quality, Safety and Improvement Committee |  |  |  |  |  |  |  |  |  |  |  |
| Inherent Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  | 10/05/23 |  |  |  | Likelihood: |  |  | 4 | Impact: | 5 | Score: |  | 20 |  |  |
| Risk Score |  |  |  |  |  |  |  |  |  |  | Risk Decision |  |  | Delivery Confidence Assessment |  |  |  |
| Current Risk |  |  |  |  | Target Risk |  |  |  |  |  | Treat |  |  | AMBER |  |  |  |
| Likelihood |  | Impact |  | 12 | Likelihood |  |  | Impact | 6 |  |  |  |  |  |  |  |  |
| 3 |  | 4 |  |  | 2 |  |  | 3 |  |  |  |  |  |  |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 3.1 | Behavioural Science Unit to provide specialist expertise on behavioural insights integration into the programmes of work, and develop the application of it, to improve and protect health & wellbeing in Wales | Director of Policy and International Health | Performance monitoring of IMTP delivery through Leadership Team KRIC meeting notes | X | X | X | X |  |
| SR 3.2 | Time to Talk Public Health Survey to enable regular public engagement to inform public health policy and practice | Director of Policy and International Health | Performance monitoring of IMTP delivery through Leadership Team | X | X | X |  |  |
| SR 3.3 | Behavioural insights integration into the work of population health programmes and public communications | National Director of Health and Well-being | Performance monitoring of IMTP delivery through Leadership Team | X | X | X |  |  |
| SR 3.4 | Robust communications plans underpinned by evidence-based methodologies in place for planned campaigns | Deputy Chief Executive and Director of Operations and Finance | Annual plan of communications campaigns Evaluation of public campaigns and sharing of learnings | X | X |  |  |  |
| SR 3.5 | Provision of timely, accurate and relevant risk communications in response to emerging public health issues. | Deputy Chief Executive and Director of Operations and Finance | Incident Management Team or Outbreak Control Team notes Significant issues are discussed with Executive and at Board | X |  | X |  | X |
| SR 3.6 | The Public Health Young Ambassadors group as a conduit to enable conversations to take place with young people | Director of Quality, Nursing and Allied Health Professionals | Briefing notes following Residential Board minutes |  |  | X |  | X |

| Action plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 3.1 | Ongoing engagement with the public, our service users and stakeholders to ensure we understand needs and priorities, and obtain feedback on the impact of our work |  | Further development of public and service user engagement through Civica system | Director of Quality, Nursing and Allied Health Professionals | March 2024 | July 2023 update - A refresh to the organisation’s approach to engagement is underway, with support from the I&I Hub and cross-directorate working. This will include reviewing the process and quality of questionnaires / surveys developed and published by PHW. This will create accessible options for data capture and distributing learning across the organisation |
| AP 3.2 (see AP1.5) | Co-ordination of activity to understand the needs of underserved populations |  | Establish an Inclusion Health programme in PHW | National Director of Health Protection and Screening Services | December 2023 | July 2023 update - Progress is challenged by support of DDHPSS to Public Inquiry Board. Scoping Report deferred to September. |
| AP 3.3 | Engagement of our population to actively manage our own health and well-being and associated risks |  | Work with Welsh Government and Health Boards to engage the population and subsets of the population to fully engage in and control risks to their own health and well-being, including understanding resources required to achieve this. | Director of Policy and International Health, National Director of Health and Well-being, National Director of Health Protection and Screening Services | March 2024 | July 2023 update - The Behavioural Science Unit has published and continues to develop tools to enable public engagement with their health and wellbeing. The Unit is working across Directorates to embed behavioural science in the delivery of their work and contributed to the Welsh Government ‘waiting well’ initiative. |
| AP 3.4 | See actions for risk 6 |  |  |  |  |  |

| Risk 4 |  | There is a risk of weakness in our organisational health, including our culture, capacity, capabilities and governance. Caused by sub-optimal leadership, management and engagement. Resulting in low staff wellbeing and morale, failure to recruit and retain our staff and ineffective performance across one or more of our strategic priorities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Owner’s Overview Assessment Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The organisation is implementing QOS incorporating governance system mapping and controls and has actions in place to mitigate the risk and close the gaps in assurance. POD have clear actions in the IMTP which relate directly to this risk, i.e., Work to understand current v desired culture, launching and embedding our ‘Being Our Best’ framework and a road map to deliver the people promise. Workforce planning is also part of the IMTP deliverables and a critical component in addressing this risk. Collaborative working between Planning, POD and Communication functions will contribute to improved methods to launch, land and embed related products/messaging. A Leadership and Management Development Academy has also been launched, which together with the actions outlined in this plan, will support improved leadership, Management and engagement. Our Board and Committees are constituted in accordance with our Standing Orders and Scheme of Delegations. The functions of the Board are delivered in line with the Board Etiquette Protocol with external assurance from Audit Wales on performance. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sponsor and Assurance Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Executive Sponsor |  |  |  |  |  |  | Neil Lewis, Director of People and OD Contributors: John Boulton, Director for NHS Quality Improvement and Patient Safety Rhiannon Beaumont-Wood, Exec Dir Quality, Nursing and Allied Health Professionals Huw George, Deputy Chief Executive and Exec Dir Ops and Finance Paul Veysey, Board Secretary and Head of Board Business Unit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assurance Group |  |  |  |  |  |  | People and Organisational Development Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inherent Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  | 16/5/23 |  |  |  | Likelihood: |  |  |  | 5 | Impact: |  | 5 | Score: |  | 25 |  |  |  |  |  |  |  |
| Risk Score |  |  |  |  |  |  |  |  |  |  |  |  | Risk Decision |  |  |  | Delivery Confidence Assessment |  |  |  |  |  |  |  |  |
| Current Risk |  |  |  |  |  | Target Risk |  |  |  |  |  |  | Treat |  |  |  | AMBER |  |  |  |  |  |  |  |  |
| Likelihood |  |  | Impact |  | 16 | Likelihood |  |  | Impact |  | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  | 4 |  |  | 3 |  |  | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EXISTING CONTROLS |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SOURCES OF ASSURANCE |  |  |  |  |  | Level at which the Assurance is provided to |  |  |  |  |  |  |
| No. |  | Control |  |  |  |  |  |  |  |  | Exec Owner |  |  |  |  |  |  |  |  |  | Team / Division / Project /Programme |  | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |  |
| SR 4.1 |  | Compliance with Information Governance policy and supporting procedures |  |  |  |  |  |  |  |  | Rhiannon Beaumont-Wood, Executive Director of Quality and Nursing |  |  |  | IG performance report |  |  |  |  |  |  |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Information Governance toolkit |  |  |  |  |  |  |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Information Governance Group assurance to Audit and Corporate Governance Committee |  |  |  |  |  |  |  |  | X |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Information Asset Register |  |  |  |  |  |  |  |  | X |  |  |  |
| SR 4.2 |  | Compliance with Risk Management policy, procedure and other written control documents (protocol) |  |  |  |  |  |  |  |  | Rhiannon Beaumont-Wood, Executive Director of Quality and Nursing |  |  |  | Assurance reports on Strategic Risks |  |  |  |  |  |  |  |  |  |  | X |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Strategic Risk Register and Corporate Risk Register reports to Board |  |  |  |  |  |  |  |  |  | X | X |  |
| SR 4.3 |  | Planned People and OD Committee Meetings to review progress v plan (including dashboard data on workforce trends) and consider emerging threats |  |  |  |  |  |  |  |  | Neil Lewis, Director of People & OD |  |  |  | PODCOM Minutes from meetings |  |  |  |  |  |  |  |  |  | X |  |  |
| SR 4.4 |  | Refreshed Long Term |  |  |  |  |  |  |  |  | Deputy Chief Executive and Exec Dir Ops and Finance |  |  |  | IMTP Reporting process |  |  |  |  |  |  |  |  | X |  |  |  |
| SR 4.5 |  | People Strategy and IMTP |  |  |  |  |  |  |  |  | Neil Lewis, Director of People & OD |  |  |  | Reporting against IMTP Milestones |  |  |  |  |  |  |  |  | X |  |  |  |
| SR 4.6 |  | Compliance with Standing Orders, Scheme of Delegation and Board Etiquette Protocol |  |  |  |  |  |  |  |  | Paul Veysey, Board Secretary and Head of the Board Business Unit |  |  |  | Internal Audit Audit Wales Annual Accountability Reporting to Welsh Government |  |  |  |  |  |  |  |  |  |  | X X X |  |

| Action plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 4.1 | Organisational-wide Records Management System |  | Design and implement Records Management System across organisation | Rhiannon Beaumont-Wood, Executive Director of Quality and Nursing | 30/03/24 |  |
|  |  |  | Approved Records Management policies and procedures | Rhiannon Beaumont-Wood, Executive Director of Quality and Nursing | 30/09/23 |  |
| AP 4.2 | Standardised approach to Governance and Quality Management |  | Implement Quality as an Organisational Strategy | John Boulton |  |  |
|  |  |  | Implement year 2 of Integrated Governance implementation plan | Rhiannon Beaumont-Wood, Executive Director of Quality and Nursing | 30/03/24 |  |
| AP 4.3 | A co designed / developed high- level plan which will deliver desired culture |  | Establish a high-level plan which will deliver desired culture (to include communication and engagement aspects) | Neil Lewis -Director People and OD | 30/6/23 | 09/07/2023 A high-level plan is in place with initial actions complete / ongoing: - Directorates will be briefed on location outcomes over the summer and asked to identify local culture advocates - Intranet content is live - Work to connect purpose, LTS, culture, values and behaviour is being undertaken at LT level. - Leading with impact workshops are being scoped to run in 2023-2024 |
|  |  |  | Develop KPI’s to measure how well Managers are engaging their direct reports and use these as part of regular 1-1 reviews | Neil Lewis -Director People and OD | 28/9/23 |  |
| AP 4.4 | Protected time at Exec level to review culture and effectiveness of associated plan/actions. |  | Dedicate an agreed number of Strategic BET Meetings to review progress v plan and impact of culture plan. | Neil Lewis -Director People and OD | 30/6/23 |  |
| AP 4.5 | A strategic and systemic approach to employee engagement |  | Development of a strategic and systemic approach to employee engagement | Neil Lewis -Director People and OD | 31/12/23 | Due date moved forward three months due to staff survey being moved from summer 2023 to autumn 2023 |
|  |  |  | Systematic reviews of Staff survey responses and delivery of action plans | Neil Lewis -Director People and OD | 31/12/23 | Due date moved froward three months due to staff survey being moved from summer 2023 to autumn 2023 |
| AP 4.6 | Ownership of organisation wide WFP process to ensure delivery of capacity and capability risks addresses |  | Directorates to commit to WFP process and take action to close workforce risks | TBD | Ongoing | 09/07/2023 A two-year, high-level workforce plan is in place. Members of POD are working with directorates to ensure the next key milestone, (ensure resourcing plans are in place for all critical roles) is completed by end of September 2023. |

| Risk 5 | There is a risk that we insufficiently prevent, plan for and respond to emerging external threats to public health. Caused by insufficient horizon scanning, forecasting, use of data/digital tools and planning/training/exercising for response. Resulting in suboptimal responses to near-term incidents (including but not limited to infectious disease) and longer-term emerging risks to public health. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Owner’s Overview Assessment Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The current risk score is at the inherent risk level. There are existing controls relating to: Emergency planning and learning from incidents and outbreaks, including the COVID pandemic; workforce planning and development for response; training and exercising; and horizon-scanning activities. However, there is more action required to reduce the impact of external threats, through developing an understanding of roles and responsibilities of each component of the response architecture and the health protection competencies that need to be held in reserve for surge response. The learning from COVID response is not yet complete and the Public Inquiry is underway. These will provide more information to improve response to external threats. Action is also required to join up the horizon-scanning efforts across the organisation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sponsor and Assurance Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Executive Sponsor |  |  |  |  | Meng Khaw, National Director of Health Protection and Screening Services Contributors: Iain Bell, Director of Knowledge and Research Sumina Azam, Director of Policy and International Health / WHOCC |  |  |  |  |  |  |  |  |  |  |  |  |
| Assurance Group |  |  |  |  | Quality, Safety and Improvement Committee |  |  |  |  |  |  |  |  |  |  |  |  |
| Inherent Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  | 15 May 2023 |  |  |  | Likelihood: |  |  | 3 | Impact: | 4 | Score: |  | 12 |  |  |
| Risk Score |  |  |  |  |  |  |  |  |  |  | Risk Decision |  |  | Delivery Confidence Assessment |  |  |  |
| Current Risk |  |  |  |  |  | Target Risk |  |  |  |  | Treat |  |  | AMBER |  |  |  |
| Likelihood |  | Impact |  | 12 |  | Likelihood |  | Impact | 6 |  |  |  |  |  |  |  |  |
| 3 |  | 4 |  |  |  | 3 |  | 2 |  |  |  |  |  |  |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 5.1 | Horizon Scanning | National Director of Health Protection and Screening Services | IHR reports | X | X |  |  |  |
|  |  |  | UKHSA sources | X | X |  |  |  |
|  |  |  | PHW horizon scans (incl EPRR Work with National Security Risk Assessment (NSRA)) | X | X |  |  |  |
|  |  |  | Genomics | X | X |  |  |  |
|  |  |  | Links with APHA and other agencies | X | X |  |  |  |
|  |  |  | Weekly meetings with HPT | X | X |  |  |  |
|  |  |  | UKHSA daily emerging infections horizon scanning results | X | X |  |  |  |
|  |  |  | GEZI Wales horizon scans every 2 weeks | X | X |  |  |  |
| SR 5.2 | Forecasting and use of data/digital tools | National Director of Health Protection and Screening Services | Exceedance algorithms | X | X |  |  |  |
|  |  |  | Reports including exposures, climate and environmental determinants. | X | X |  |  |  |
|  |  |  | Short/medium term models working with academic partners. | X | X |  |  |  |
| SR 5.3 | Planning/training/exercising for response | National Director of Health Protection and Screening Services | PHW Emergency Response Plan | X | X | X | X | X |
|  |  |  | Communicable Disease Plan for Wales | X | X | X | X | X |
|  |  |  | Multi-Agency Plans for Emergencies (Contributor) | X | X |  |  |  |
|  |  |  | Emergency Planning & Business Continuity Group Meetings (Quarterly) | X | X |  |  |  |
|  |  |  | Local Resilience Fora (LRF) Meetings | X | X | X |  |  |
|  |  |  | Wales Resilience Partnership Team Meetings (Quarterly) | X | X |  |  |  |
|  |  |  | Wales Resilience Forum Meetings (Quarterly) | X | X |  |  |  |
|  |  |  | 4 Nations Public Health (PH) Emergency Preparedness, Resilience & Response (EPRR) Meetings (Quarterly) | X | X |  |  |  |
|  |  |  | PHW EPRR Training Prospectus | X | X |  |  |  |
|  |  |  | LRF Training Prospectus | X | X |  |  |  |
|  |  |  | Wales Learning & Development Group (Exercises) | X | X |  |  |  |
|  |  |  | PHW Annual Assurance Return to Welsh Government on EPRR | X | X | X | X | X |
| SR 5.4 | Debrief and learning from incidents and outbreaks | National Director of Health Protection and Screening Services | Organisational debrief and learning from the response to the COVID pandemic and other incidents and outbreaks | x | x |  |  |  |
| SR 5.5 | Health Impact Assessments to understand potential threats and opportunities to health from policies and programmes, as well as external events. | Director of Policy and International Health | Performance monitoring of IMTP delivery through Leadership Team |  | X | X |  |  |
| SR 5.6 | Development of tools and products to implement Futures approaches | Director of Policy and International Health | Performance monitoring of IMTP delivery through Leadership Team |  | X | X |  |  |

| Action plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 5.1 | Enhancement of current genomics work required | CW | Expand the range of genomics horizon scanning. | National Director of Health Protection and Screening Services | March 2024 |  |
|  |  | HW | Assess risk, vulnerability, capacity, exposure, hazard characteristics and their possible sequential effects on PHW. Consider the organisations capability and capacity to respond to, and mitigate, identified risks detailed within the NSRA. PHW will continue to engage and work with the Wales Risk Group and contribute to the development of LRF Community Risk Registers. | National Director of Health Protection and Screening Services | March 2024 | 30/06/23: Work ongoing with 4no. LRFs across Wales and Wales Risk Group to interpret the NSRA and assess risks pertinent regionally for inclusion revised LRF Community Risk Registers. |
| AP 5.2 | Enhancement of exceedance algorithms required | CW | Further development and Operationalisation. | National Director of Health Protection and Screening Services | March 2024 |  |
| AP 5.3 | Work required to enhance planning activity | HW | Obtain Board approval for PHW Emergency Response Plan (V.3) | National Director of Health Protection and Screening Services | May 2023 | 30/06/23: Action Complete; approved by Board (25.05.23). |
|  |  | HW | Review and update supporting documentation for the PHW Emergency Response Plan (V.3) | National Director of Health Protection and Screening Services | October 2023 | 30/06/23: Work commenced to Review and update supporting documentation. |
|  |  | AJ | Review and update the Communicable Disease Plan for Wales | National Director of Health Protection and Screening Services | November 2023 | 30/06/23: Mult-agency planning begun, workstreams established to review and update core sections of the document. |
|  |  | HW | Work with partners to review and update multi-agency plans for emergencies. | National Director of Health Protection and Screening Services | March 2024 | 30/06/23: Work ongoing with 4no. LRFs and other partners. Recent work completed on various COMAH Plans across Wales. |
| AP 5.4 | Ensure PHW engages with and participates in all appropriate EPRR training & exercise opportunities | HW | Identify opportunities to participate in Exercise Doll House & Exercise Astral Bend. (Exercising PHW staff in multi-agency command and control environment) | National Director of Health Protection and Screening Services | July 2023 & September 2023 | 30/06/23: PHW agreement to participate in Exercise Doll House, Strategic Response Director on initial SCG meeting, Strategic Liaison Officer on following SCG meetings. |
|  |  |  | Review and update PHW EPRR Training Prospectus to reflect the updated PHW Emergency Response Plan (V.3). | National Director of Health Protection and Screening Services | October 2023 | 30/06/23: Work commenced to provide awareness sessions throughout July 23. |
|  |  |  | Ensure strategic attendance at 5no. Wales Gold IV Courses. | National Director of Health Protection and Screening Services | October 2023 | 30/06/23: Strategic attendance at all Wales Gold IV courses in 2023 to date. 1no. Additional course planned for October 2023. |
|  |  |  | Plan and deliver an exercise for the updated PHW Emergency Response Plan (V.3) | National Director of Health Protection and Screening Services | November 2023 | 30/06/23: Work commenced to plan deliver the exercise. |
|  |  | HW AJ | Support the planning and delivery of an exercise for the updated Communicable Disease Plan for Wales. | National Director of Health Protection and Screening Services | March 2024 | 30/06/23: Support provided for workstream established to review and update Section 07 of the document. |
| AP 5.5 | Ensure PHW has a sustainable mechanism for receipt of Major Incident notifications. | HW AJ | Identify and implement a sustainable mechanism for receipt of Major Incident notifications | National Director of Health Protection and Screening Services | July 2023 | 11/05/23: Changes to alerting processes utilised by Welsh Ambulance Service NHS Trust (WAST) and other partners mean that the current arrangements to receipt these messages will fail. 30/06/23: Review of options undertaken with a recommended proposal providing robust mitigation to the issues identified to be considered. |
| AP 5.6 | Ensure lessons are identified from incidents and outbreaks, including the COVID pandemic | HW AJ | Carry out debrief sessions to identify lessons from the COVID pandemic, including horizon scanning, surge response and implementation at scale. | National Director of Health Protection and Screening Services | December 2023 | 30/06/23: PHW Learning Event held for the Early Phases of COVID-19 Response involving Gold Group & Incident Directors (10.05.23). |
| AP 5.7 | Systematic organisational approach to embedding Horizon Scanning |  | Strategic BET development session to explore mechanisms and processes for embedding horizon scanning | Director of Policy and International Health | July 2023 |  |
| AP 5.8 | Update prevalence of disease and projections of future disease levels in Wales |  | To systematically analyse the prevalence of disease, project these levels into the future and assess our current interventions and what more needs to be done | Director of Knowledge and Research | Dec 2023 |  |

| Risk 6 | There is a risk that we fail to deliver excellent public health services, including on screening, infection and health protection. Caused by weakness in clinical and health protection processes, specialist workforce capacity and capabilities, innovation and/or capital investment. Resulting in inadequate provision, responsiveness or uptake of services, poor individual patient and population outcomes and failure to meet quality standards. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Risk Owner’s Overview Assessment Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The current risk score is at the inherent risk level. However, over the past year, this had the potential to be higher resulting from a number of significant health protection incidents had increased (such as monkeypox, the exceedance of STEC and group A streptococcal infections), but those threats have now stabilised. There are existing controls relating to: workforce planning and development; mitigation of impacts of unexpected health threats through the establishment of effective systems and processes; and strengthening governance arrangements to ensure excellent service delivery in HPSS through implementation of the long-term strategy. Each of the three divisions in HPSS directorate are likely to score differently if reviewed independently and this will be reflected in divisional and directorate risk registers. This is a known dynamic risk and as such will be actively monitored and managed in HPSS at both division and directorate levels. As we look to the 2023 / 24 planning cycle this risk is likely to endure and the action plans during this months review reflect dates into next year. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sponsor and Assurance Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Executive Sponsor |  |  |  |  |  | Meng Khaw, National Director of Health Protection and Screening Services Contributors: Rhiannon Beaumont-Wood, Exec Dir Quality, Nursing and Allied Health Professionals |  |  |  |  |  |  |  |  |  |  |  |
| Assurance Group |  |  |  |  |  | Quality, Safety and Improvement Committee |  |  |  |  |  |  |  |  |  |  |  |
| Inherent Risk |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  | 15 May 2023 |  |  |  | Likelihood: |  |  | 3 | Impact: | 3 | Score: |  | 9 |  |  |
| Risk Score |  |  |  |  |  |  |  |  |  |  | Risk Decision |  |  | Delivery Confidence Assessment |  |  |  |
| Current Risk |  |  |  |  | Target Risk |  |  |  |  |  | Treat |  |  | GREEN |  |  |  |
| Likelihood |  | Impact |  | 9 | Likelihood |  |  | Impact | 6 |  |  |  |  |  |  |  |  |
| 3 |  | 3 |  |  | 3 |  |  | 2 |  |  |  |  |  |  |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 6.1 | Overview and scrutiny of workforce capacity and capability is provided through clear governance arrangements with divisional SMTs and DLT | National Director of Health Protection and Screening Services | Divisional SMT meeting and minutes | X | X |  |  |  |
|  |  |  | DLT meetings and minutes |  | X |  |  |  |
|  |  |  | Escalation to BET with meetings and minutes |  | X | X |  |  |
|  |  |  | Divisional, Directorate and Corporate Risk Registers actively updated and risks escalated as appropriate | X | X | X | X | X |
| SR 6.2 | Implementation of Business Continuity Arrangements where required and where appropriate | National Director of Health Protection and Screening Services | Business Continuity Action Plans for HPSS divisions | X | X | X |  |  |
|  |  |  | Emergency Planning and Business Continuity Group Meeting minutes |  | X |  |  |  |
|  |  |  | Training and Exercise reports to Emergency Planning and Business Continuity Group | X | X |  |  |  |
|  |  |  | Emergency Planning and Business Continuity Documentation (regular review and update) | X | X |  | X |  |
|  |  |  | Ability to sustain response to health threats |  | X |  |  |  |
| SR 6.3 | Utilisation and development of Policies and Procedures to enable effective and efficient service delivery, including Standard Operating Procedures and Protocols. | National Director of Health Protection and Screening Services | Corporate Policy and Control Document Reviews – corporate register update reports | X | X | X | X | X |
|  |  |  | Health Protection Division – Standard Operating Procedures (document development, review and approval) | X | X |  |  |  |
|  |  |  | Infection Division – Standard Operating Procedures (document development, review and approval), alignment to UKAS accreditation requirements. | X | X | X | X |  |
|  |  |  | Screening Division –For each of the screening programmes - Standard Operating Procedures (document development, review and approval) | X | X |  |  |  |
|  |  |  | Reports to Quality, Safety and Improvement Committee |  | X | X | X |  |
|  |  |  | Action Plan and Reports – Divisional Senior Management Teams | X |  |  |  |  |
| SR 6.4 | Uphold high professional standards: Professional Regulation – Medical, Nursing and Multi-Disciplinary Staff | Executive Medical Director Executive Director of Quality and Nursing and Allied Health Professionals | Medical, Nursing and Multi-Disciplinary Staff Revalidation - Annual Report to People and Organisational Development Committee / Quality, Safety and Improvement Committee |  |  |  | x |  |
|  |  |  | Quality review visit by Medical and Multi-Disciplinary Revalidation support unit |  |  | X | X |  |
|  |  |  | Quality Indicators Performance Monitoring | X | X | X | X |  |
|  |  |  | Monitor Specialist Registration and Revalidation |  | X | X | X | X |
|  |  |  | Medical, Nursing and Multi-Disciplinary Appraisal Process – Quality Indicator |  | X | X | X | X |
|  |  |  | Medical Job Planning Process – Quality Indicator |  |  | X |  | X |
| SR 6.5 | Established Directorate Financial Management Systems and Processes | National Director of Health Protection and Screening Services | Directorate Finance reports to Directorate Management Team meeting (monthly). Supported by the Business Operations Meeting (BOM) | x | x |  |  |  |
|  |  |  | Divisional Finance reports to SMT | X |  |  |  |  |
|  |  |  | Executive Director Reports (to Executive and Board) |  |  | X |  | X |
|  |  |  | Mid and End of Year Review Reports (Executive scrutiny) |  |  | X |  | X |
| SR 6.6 | Implementation of learning from incidents | National Director of Health Protection and Screening Services | Datix reporting at programme and divisional level | X | X | X |  |  |
|  |  |  | Putting Things Right - Quarterly Alert Exception Report (Quality, Safety and Improvement Committee) |  |  |  | X |  |
|  |  |  | National Reportable Incident Reporting (Quarterly) to Quality, Safety and Improvement Committee |  |  | X | X |  |
| SR 6.7 | Surveillance of health threats to inform timely and effective response | National Director of Health Protection and Screening Services | Communicable disease surveillance reports | X | X |  |  |  |
|  |  |  | Exceedance reports and protocols for escalation and response | X | X | X | X |  |
|  |  |  | Agreed criteria for escalation (reviewed on an annual basis) | X | X |  |  |  |
|  |  |  | Health Protection Situational Awareness Reports – (monthly report to Executive) | X | X | X |  | X |
| SR 6.8 | Development of Workforce Plans for each Division and established processes to enable effective Recruitment | National Director of Health Protection and Screening Services | Reports of progress against developed Workforce Plans | X | X |  |  |  |
|  |  |  | Reports to the People and Organisational Development Committee |  |  |  | X |  |
|  |  |  | Directorate and Divisional-level workforce plans |  | X |  |  |  |
| SR 6.9 | Compliance with Infection control policies, procedures and related statutory and mandatory training Compliance with National Guidelines and Standard Operating procedures in place for IPC | Executive Director of Quality and Nursing and Allied Health Professionals | IPC Audit plan and Environmental Audit Programme |  |  |  | X |  |
|  |  |  | IPC group assurance reports to QSIC |  |  |  | X |  |
|  |  |  | IPC Risk Register |  |  | X |  |  |
|  |  |  | Annual clinical Audit Plan |  |  |  | X |  |
| SR 6.10 | Putting Things Right Policies and Procedures Regular monitoring of incidents to identify immediate action required | Executive Director of Quality and Nursing and Allied Health Professionals | Monthly Reporting of patient service user experience including incidents, complaints and claims |  |  |  | X |  |
|  |  |  | Quality Reviews of Incidents and associated action plans |  | X |  |  |  |
|  |  |  | Thematic reviews on areas of concern |  |  |  | X |  |

| Action plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 6.1 | NHAIS is being decommissioned by England and we currently rely on NHAIS to select breast screening cohort. Reliant on one member of staff who has detailed knowledge of NHAIS. | SH | Implementation of BSS select for Breast Screening Programme to maintain cohort selection for breast screening. Working group with NHS England colleagues to progress this change | Deputy Chief Executive / Executive Director of Finance and Operations National Director of Health Protection and Screening Services | March 2024 | 20/06/23 Meetings progressing with NHS England and continuing to scope and explore this solution and also taking forward an in-house alternative solution (NHS England aware). There are concerns for timescales with either option. Discovery work taking place with programme and digital team which is being taken forward internally. The interviews for companies to take forward an in-house solution on 29 June and therefore will know in a few weeks if this is a viable option. Working to implementation of solution by end March 2024 at latest. |
| AP 6.2 | Recovery of the Breast Screening Programme is impacted by difficulty in recruiting specialist clinical staff to undertake reading of mammograms and assessment clinics. | SH | Recruitment processes underway for breast clinician role in North Wales. Planned recruitment in Southeast Wales for radiologist working closely with Health Boards. Planned retirement in 2023 will increase issue in North Wales and working with HB to explore potential ways forward. | National Director of Health Protection and Screening Services | March 2024 | 20/06/23 Interviews for trainee Breast Clinician in the North w/c 22nd June. Joint post with BCU going out to advert currently with a further joint post approved just awaiting recruitment process to start. Joint Radiologist post with C & V due to start in July 23. |
| AP 6.3 | Sustainable provision of clinical infection services | RH DH | Continue to recruit to consultant posts; Deliver changes that will make the service more attractive including recruitment of Specialty and Specialist Doctors as well as Physician Associates, Clinical Scientists and Specialist Nurses. | National Director of Health Protection and Screening Services | Ongoing | Remote consultant support is being trialled and has proven to be beneficial and extended to end of financial year. Service continues to search for additional workforce opportunities. |
|  |  |  | Set out service requirements in a business case and single establishment control submission as contribution towards the Directorate budget realignment work. | National Director of Health Protection and Screening Services | May 2023 | 16/06/23 – Business Case submitted to National Director of Health Protection & Screening Services |
|  |  |  | Complete training competencies for all staff who are able/required to deliver OOH services | National Director of Health Protection and Screening Services | September 2023 | 16/06/23 – Training resources continue to be subject to SMT oversight for OOH competencies. Individual focussed activities undertaken |
|  |  |  | Complete Syndromic Molecular Procurement project to include: - Respiratory - GI - AMR - Bone and joints - BBV - Sexual Health | National Director of Health Protection and Screening Services | October 2023 | 16/06/23 - advice from NWSSP is that PHW is able to access the NHS Supply Chain contract allowing direct awards. The project team are finalising requirements and approach to confirm at Infection SMT. |
| AP 6.4 | Resilient Out of Hours Acute Health Protection Service | GS EM | Reviewing the model of service delivery to test resilience and sustainability | National Director of Health Protection and Screening Services | July 2023 | 30/6/23 – Implementation group work underway with the aim to go live on 01 August 2023 |
| AP 6.5 | Surge Plan for Acute Health Protection | GS EM | Agreed oversight and surge plan for Acute Health Protection | National Director of Health Protection and Screening Services | September 2023 | 30/6/23 – project plan to develop Surge Plan progressing as anticipated |
| AP 6.6 | Clinical Governance Framework |  | Approved and published Clinical Governance Framework | Executive Director of Quality and Nursing and Allied Health Professionals | July 2023 |  |
|  |  |  | Progress to approval and implementation of Career Framework for regulated health professionals (non-medical) | Executive Director of Quality and Nursing and Allied Health Professionals | May 2023 |  |
|  |  |  | Progress to approval and implementation of the organisational Clinical Supervision Framework | Executive Director of Quality and Nursing and Allied Health Professionals | May 2023 |  |
| AP 6.7 | Key lines of enquiry from Welsh Government to support Quality Standards reporting |  | Obtain key lines of enquiry from Welsh Government, implement once published, and complete self assessment. | Executive Director of Quality and Nursing and Allied Health Professionals | Sept 23 |  |
|  |  |  | Identify improvement plan following self-assessment for 2024/25. | Executive Director of Quality and Nursing and Allied Health Professionals | March 24 |  |
|  |  |  | Complete first Annual Quality Report | Executive Director of Quality and Nursing and Allied Health Professionals | March 24 |  |