Risk Owner’s Overview Assessment Status

The organisation is still awaiting Ministerial approval of the Board approved IMTP which takes account of the current known threats. We will continue to monitor the impact of the IMTP to respond to potential emerging geopolitical, socio-economic and health threats. The development of a key data dash board to monitor the health of the nation will provide information to inform any new or additional interventions to respond to emerging health and wellbeing needs. We have met with the CMO and officials in relation to the cost of living crisis and committed to developing a public health approach to it. This is being progressed in a coordinated way across the organisation and will also consider how we best support our own staff. We continue to have regular meetings with Minister’s and officials and we are actively engaged with the WHO and IANPHI in order to help identify, assess and support current and emerging threats.

| Risk 1 | There is a risk that Public Health Wales will not be sufficiently focused, agile and responsive in discharging our functions, caused by the unpredictable and changing nature of the current and emerging geopolitical, socio-economic and health threats, resulting in an inability to tackle the population health challenges in a sustainable way. |
| --- | --- |

| Sponsor and Assurance Group |  |
| --- | --- |
| Executive Sponsor | Tracey Cooper |
| Assuring Group | Quality, Safety and Improvement Committee |

| Inherent Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | 10.05.2022 | Likelihood: | 4 | Impact: | 4 | Score: | 16 |

| Risk Score |  |  |  |  |  | Risk Decision | Delivery Confidence Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Current Risk |  |  | Target risk |  |  | Treat | Amber |
| Likelihood | Impact | 16 | Likelihood | Impact | 12 |  |  |
| 4 | 4 |  | 3 | 4 |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 1.1 | Regular Business Executive Team Meetings to review implementation of IMTP and emerging threats | Chief Executive/All Execs | Business Executive Team Minutes |  |  | X | X | X |
| SR 1.2 | Embedded management of health protection response for COVID within HPSS Directorate Leadership Team | National Director of Screening and Health Protection Services and Medical Director | HPSS DLT minutes and COVID-Ex minutes |  | X | X |  |  |
|  |  |  | COVID-EX minutes |  | X |  |  |  |
| SR 1.3 | Incident Management Teams in place for Ukraine conflict in PHW and in UKHSA for UK | National Director of Screening and Health Protection Services and Medical Director | Minutes of IMT and summary |  | X |  |  |  |
|  |  |  | Minutes of UKHSA IMT and summary |  | X | X |  |  |
| SR 1.4 | Regular meetings with Welsh Government Minister(s) and officials which include discussions in relation to existing and emerging health and socio-economic threats in Wales | Chief Executive | Actions arising following meetings as appropriate |  | X | X |  |  |
| SR 1.5 | Formalised meetings with WHO Collaborating Centre and WHO | Director of Policy Research and Development, Policy, Research and International Development | Minutes of WHOCC and WHO meetings |  |  |  |  |  |
| SR 1.6 | Weekly meetings with a number of IANPHI European Institutes and Ukraine PH Institute | Chief Executive/MB | Notes of meetings at exec lead/BET level as appropriate |  |  |  |  |  |

| Action Plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 1.1 | Longer term planning for new and emerging threats incorporated into a revised Long Term Strategy to develop a coherent and synergistic approach to multi-shocks. |  | Development and approval of new Long Term Strategy | HG | April 2023 | Ongoing development of the Long Term Strategy and engagement with staff and partners. |
| AP 1.2 | More formalised series of collective public health ‘threat’ assessment to include health, environmental, socio-economic and geopolitical threats, to be incorporated into Strategic Business Executive Team business. |  | To be considered by BET with the view of identifying a lead (s) Exec to coordinate a regularised approach to multi-shock public health threat assessment – including domestic and global population health threats. | TC | Ongoing | Cost of living crisis presented by Sumina Azam (SA) and Iain Bell (IB) at Strategic Executive Team meeting on 28.6.22. Actions agreed for SA, IB and Angela Jones to coordinate cross organisational activity to develop a ‘Public Health Approach to the cost of living crisis. |
|  |  |  | Develop a rapid re-prioritisation planning process if required that is triggered by significant threats that require substantial in-year focus/resource | HG | To be confirmed | This will be informed by the population health dashboard that will be considered a part of our Integrated Performance report. This is being presented at a Board development session on the 30.6.22. |
|  |  |  | Joint meetings with WG colleagues to consider this with inclusion of international partners as appropriate | MK/MB/SA |  | WHO roundtable meeting being arranged 9.22 to consider this with focus on cost of living crisis. Establishing monthly meetings with CMO and his team and some of our Exec team for a more strategic approach to population health action and will include emerging threats |
|  |  |  | International Horizon Scanning reports to consider new and emerging global public health threats no less than twice a year | MB | Ongoing horizon scanning. Focus on emerging threats to be confirmed. |  |

Risk Owner’s Overview Assessment Status

Each of the three divisions in HPSS directorate are likely score differently if looked at independently and will be reflecting this in their divisional and the directorate RR’s This is a known dynamic risk and as such will be actively monitored and managed in HPSS at both division and directorate levels, feeding into this strategic RR. The risk score is currently sitting above the already significant inherent risk level. This is largely due to a range of enhanced public health incidents and the recovery and transition activity relating to transition from pandemic to endemic COVID 19 management. There are existing controls relating to workforce and a lesser degree health threats and management plans detailed at divisional level which are monitored and reported through the Directorate Leadership Team construct and on to PHW governance routes where appropriate – e.g. Screening Programme Recovery Plan.

| Risk 2 | There is a risk that Public Health Wales will not deliver its plans for delivering excellent services for population screening, health protection and infection caused by uncertainty of the impact of current and future health threats and lack of specialist workforce, resulting in inability to prioritise service delivery and transform models of care. |
| --- | --- |

| Sponsor and Assurance Group |  |
| --- | --- |
| Executive Sponsor | National Director Health Protection and Screening Services, and Medical Director |
| Assuring Group | Quality, Safety and Improvement Committee |

| Inherent Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | 11.05.2022 (reviewed 08.07.22) | Likelihood: | 3 | Impact: | 3 | Score: | 9 |

| Risk Score |  |  |  |  |  | Risk Decision | Delivery Confidence Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Current Risk |  |  | Target risk |  |  | Treat | Amber |
| Likelihood | Impact | 12 | Likelihood | Impact | 6 |  |  |
| 4 | 3 |  | 3 | 2 |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 2.1 | Clear Governance arrangement with Senior Management Team meetings for divisions escalating up to Directorate meetings for overview and scrutiny of workforce | National Director Health Protection and Screening Services, and Medical Director | SMT meeting and minutes for divisions | X | X |  |  |  |
|  |  |  | Directorate meetings and minutes for directorate |  | X |  |  |  |
|  |  |  | Escalation to BET with meetings and minutes for BET |  | X | X |  |  |
|  |  |  | Risk Registers actively updated and risks escalated as appropriate | X | X | X | X | X |
| SR 2.2 | Business Continuity Arrangements | National Director Health Protection and Screening Services, and Medical Director | Business Continuity Action Plans for HPSS divisions | X | X | X |  |  |
|  |  |  | Emergency Planning and Business Continuity Group Meeting minutes |  | X |  |  |  |
|  |  |  | Training and Exercise reports to Emergency Planning and Business Continuity Group | X | X |  |  |  |
|  |  |  | Emergency Planning and Business Continuity Documentation (regular review and update) | X | X |  | X |  |
| SR 2.3 | Policies and Procedures *(document development, review and approval) * including Standard Operating Procedures which support the delivery of high quality services, UK Accreditation Service (UKAS) -Accreditation, | National Director Health Protection and Screening Services, and Medical Director | Corporate Policy and Control Document Reviews – corporate register update reports | X | X | X | X | X |
|  |  |  | Health Protection Division – Standard Operating Procedures (document development, review and approval) | X | X |  |  |  |
|  |  |  | Microbiology Division – Standard Operating Procedures (document development, review and approval) | X | X |  |  |  |
|  |  |  | Screening Division –For each of the screening programmes - Standard Operating Procedures (document development, review and approval) | X | X |  |  |  |
|  |  |  | Reports to Quality, Safety and Improvement Committee |  | X | X | X |  |
|  |  |  | Action Plan and Reports – Divisional Senior Management Teams | X |  |  |  |  |
|  |  |  | UKAS accreditation achieved and maintained via UKAS process |  | X | X | X |  |
| SR 2.4 | Professional Regulation – Medical, Nursing and Multi-Disciplinary Staff | National Director Health Protection and Screening Services, and Medical Director | Medical, Nursing and Multi-Disciplinary Staff Revalidation - Annual Report to People and Organisational Development Committee / Quality, Safety and Improvement Committee |  |  |  | X |  |
|  |  |  | Quality review visit by Medical and Multi-Disciplinary Revalidation support unit |  |  | X | X |  |
|  |  |  | Quality Indicators Performance Monitoring | X | X | X | X |  |
|  |  |  | Monitor registered and revalidation |  | X | X | X | X |
|  |  |  | Medical, Nursing and Multi-Disciplinary Appraisal Process – Quality Indicator |  | X | X | X | X |
|  |  |  | Medical Job Planning Process – Quality Indicator |  |  | X |  | X |
| SR 2.5 | Directorate Financial Management Systems and Processes | National Director Health Protection and Screening Services, and Medical Director | Directorate Finance reports to Directorate Management Team meeting (monthly) | X | X |  |  |  |
|  |  |  | Divisional Finance reports to SMT | X |  |  |  |  |
|  |  |  | Executive Director Reports (to Executive and Board) |  |  | X |  | X |
|  |  |  | Mid and End of Year Review Reports (Executive scrutiny) |  |  | X |  | X |
| SR 2.6 | Quality Management Systems – monitoring and early warning (including informatics and information managements systems) | National Director Health Protection and Screening Services, and Medical Director | Health and Care Standards Reporting |  | X | X | X | X |
|  |  |  | Local Audits | X | X | X | X |  |
|  |  |  | Vertical and Horizontal Audits of Microbiology Laboratory Services | X |  |  |  |  |
|  |  |  | Quality and Clinical Audit Plan |  | X | X | X |  |
|  |  |  | Mid and End of Year Review Reports (Executive scrutiny) |  | X | X |  |  |
|  |  |  | Informatics Programmes/Project Board Reports (minutes, papers and reports via Annual Plan) | X | X | X |  |  |
| SR 2.7 | Incident Reporting Management System | National Director Health Protection and Screening Services and Medical Director Executive Director Quality, Nursing and Allied Health Professionals | Datix reporting at programme and divisional level | X | X | X |  |  |
|  |  |  | Putting Things Right - Quarterly Alert Exception Report (Quality, Safety and Improvement Committee) |  |  |  | X |  |
|  |  |  | National Reportable Incident Reporting (Quarterly) to Quality, Safety and Improvement Committee |  |  | X | X |  |
| SR 2.8 | Infection, Prevention and Control Systems – monitoring and early warning | National Director Health Protection and Screening Services and Medical Director Executive Director Quality, Nursing and Allied Health Professionals | Infection Reporting Dashboard | X | X | X |  |  |
|  |  |  | Public Health Wales Infection, Prevention Control Group – minutes and papers (minutes received by Quality, Safety and Improvement Committee) | X | X | X | X |  |
|  |  |  | Agreed criteria for escalation (reviewed on an annual basis) | X | X | X |  |  |
|  |  |  | Health Protection Situational Awareness Reports – (monthly report to Executive) | X | X | X |  |  |
| SR 2.9 | Workforce/Recruitment Planning | National Director Health Protection and Screening Services and Medical Director | Reports of progress against developed Workforce Plans | X | X |  |  |  |
|  |  |  | Reports to the People and Organisational Development Committee |  |  |  | X |  |

| Action Plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 2.1 | Divisional review of existing controls |  | Work across HPSS 3 service divisions to review existing controls and identify gaps, informing the developing action plan to be signed off at Directorate level | National Director Health Protection and Screening Services, and Medical Director | July 2022 | Complete – will continue to review |
| AP 2.2 | Implementation of Cervical Screening Information Management System (CSIMS) due to NHAIS being decommissioned |  | Programme Board and Project Team established – specification agreed and near completion with end to end testing and go/no go decision date set 24 May 2022 | Deputy Chief Executive / Executive Director of Finance and Operations National Director Health Protection and Screening Services, and Medical Director | TBC | Go-live data delayed to ensure adequate testing after concerns addressed. Decision on new date for implementation due to be taken this month. |
| AP 2.3 | Implementation of BSS select for Breast Screening Programme to maintain cohort selection for breast screening due to NHAIS being decommissioned |  | Working group with NHS England colleagues to progress this change | Deputy Chief Executive / Executive Director of Finance and Operations National Director Health Protection and Screening Services, and Medical Director | March 2023 | Steady progress is being made. Dialogue continues with NHS Digital. A MoU has been drafted and both parties are currently working to refine the MoU to reflect the service requirements. |
| AP 2.4 | Recovery of the delay in timeliness of Breast Screening, Diabetic Eye Screening and Aneurysm Screening due to impact of pandemic |  | Implementation of agreed recovery plan for the remaining three screening programmes. | National Director Health Protection and Screening Services, and Medical Director | March 2024 | Recovery challenging but progressing according to divisional plans |
| AP 2.5 | Optimisation and Transformation of the Diabetic Eye Screening Programme |  | Programme is optimised to enable timely and quality programme. Transformational project taken forward to identify sustainable service model. Discovery undertaken with service users, stakeholders and staff to inform model. | National Director Health Protection and Screening Services, and Medical Director | TBC | Transformation Programme progressing with first key milestone of upgrading the DESW IT system (Optimise) complete. Programme governance and meeting structure in place and being adhered to. |
| AP 2.6 | Replacement of the Breast Screening Equipment |  | Implementation of the replacement of breast screening equipment in line with timelines – mammography equipment and mobile replacement | National Director Health Protection and Screening Services, and Medical Director | March 2024 | Project is progressing well and on time. All static units will have been upgraded by the middle of September 2022. We have received a delivery schedule for the Mobile Breast Screening Units with the first delivery expected at the end of September 2022. |
| AP 2.7 | Implementation of the re-procurement for the HPV testing equipment for Cervical Screening Programme |  | Implementation of the replacement of laboratory equipment | National Director Health Protection and Screening Services, and Medical Director | TBC | This continues to be challenging due to service and logistical issues and interdependencies including the relocation of equipment out of Magden Park to IP5 to make space for the new Roche platforms. Operational plans progressing |
| AP 2.8 | Integrated scrutiny and action planning at directorate level of available management information relating to finance, people, quality, and risk |  | Review of current meeting cadence and information flows to identify gaps and opportunities | National Director Health Protection and Screening Services, and Medical Director | July 2022 | Meeting cadence and information flow rapid review in progress. Recommendations being considered in July by HPSS DLT. |
|  |  |  | Strengthen existing system including reintroducing a directorate and business partner subgroup |  | July 2022 | Initial subgroup meeting convened drawn from past participants in April 2022 to discuss purpose and scope. Stand up of new system planned July 2022 and is on track |
| AP 2.9 | Sustainable provision of clinical infection services |  | Continue to recruit Specialty and Specialist Doctors to the Infection Service to support Consultant Workforce Recruitment of Physician Associates | National Director Health Protection and Screening Services, and Medical Director | Ongoing | In Progress |
|  |  |  | Proposal to convert non-pay Transformation funds to pay to increase number of clinical staff (Scientists and Specialist Nursing) |  | September 2022 | New action |
| AP 2.10 | Sustainable provision of laboratory diagnostics including Out of Hours |  | Review network model to optimise skill mix across multiple sites for Out of Hours working | National Director Health Protection and Screening Services, and Medical Director | December 2022 | New action |
|  |  |  | Change skill mix to include greater numbers of Associate Practitioners (Band 4s) and reduce numbers of Biomedical Support Worker (Band 2/3) to secure higher level competencies |  | March 2023 | New action |
|  |  |  | Replace the MALDI-TOF platforms in the Regional Laboratories |  | September 2022 | New action |
|  |  |  | Complete molecular testing tenders for provision of Respiratory and Central Nervous System syndromes |  | March 2023 | New action |
|  |  |  | Centralisation of Roche testing platforms at IP5 to provide i. centralised respiratory testing including COVID and ii. centralised sexual health infection testing including postal service |  | i. November 2022 April 2023 | New action |
| AP 2.11 | Out of Hours Acute Health Protection |  | Implement new central contact process | National Director Health Protection and Screening Services, and Medical Director | September 2022 | New action |
|  |  |  | Reviewing the model of service delivery to test resilience and sustainability |  | March 2023 | New action |
| AP 2.12 | Surge Plan for Acute Health Protection |  | Agreed oversight and surge plan for Acute Health Protection | National Director Health Protection and Screening Services, and Medical Director | September 2022 | New action |