|  |  |  |  | Name of Meeting Board |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Date of Meeting 30 November 2023 |  |  |
|  |  |  |  | Agenda item: 4.4 |  |  |
| Corporate Risk Register |  |  |  |  |  |  |
| Executive lead: |  | Claire Birchall, Interim Executive Director of Quality, Nursing and Allied Health Professionals |  |  |  |  |
| Author: |  | Stuart Silcox, Assistant Director of Integrated Governance Bethan Osborne, Risk Manager Eleanor Higgins, Integrated Governance Manager |  |  |  |  |
| Approval/Scrutiny route: |  | Leadership Team (2 November 2023) Business Executive Team (8 November 2023) |  |  |  |  |
| Purpose |  |  |  |  |  |  |
| This paper presents the latest version of the Corporate Risk Register (CRR) reviewed by Leadership Team and the Business Executive Team and summarises the review process followed. This includes the escalation of new risks to the CRR, the archiving of risks that have been addressed and the re-classification of some risks to issues. The paper also summarises the implementation progress of the Risk Management Development Plan (RMDP). |  |  |  |  |  |  |
| Recommendation: |  |  |  |  |  |  |
| APPROVE | CONSIDER |  | RECOMMEND |  | ADOPT | ASSURANCE |
| The Board is asked to: - Consider the latest version of the Corporate Risk Register - Take Assurance that a robust process has been followed for agreeing which existing risks are to remain on the Corporate Risk Register; identifying new risks; and archiving old risks - Take assurance on the progress being made on the Risk Management Development Plan. - Take assurance on the management of Corporate Risks within the organisation. |  |  |  |  |  |  |

| Link to Public Health Wales Strategic Plan Public Health Wales has an agreed strategic plan, which has identified seven strategic priorities and well-being objectives. This report contributes to the following: |  |
| --- | --- |
| Strategic Priority/Well-being Objective | All Strategic Priorities/Well-being Objectives |
| Strategic Priority/Well-being Objective | Choose an item. |
| Strategic Priority/Well-being Objective | Choose an item. |
| Summary impact analysis |  |
| Equality and Health Impact Assessment | N/A |
| Risk and Assurance | The paper presents the revised Corporate Risk Register |
| Health and Social Care (Quality and Engagement) (Wales) Act | N/A |
| Financial implications | N/A |
| People implications | N/A |

# Purpose / situation

This paper presents the latest version of the Corporate Risk Register (CRR) and an update on the implementation progress of the Risk Management Development Plan (RMDP).

# Background

The Board approved a re-fresh of the Long-Term Strategy in March 2023 in conjunction with a re-fresh of the organisation’s Strategic Risks.  The Business Executive Team retains oversight of Strategic Risks and has delegated oversight of Corporate Risks to the Leadership Team (LT). LT has subsequently begun to review the Corporate Risks alongside the refreshed Long-Term Strategy and Operational Plan.

This is an iterative process and the Risk Management Team continue to work with the LT to bring the CRR fully up to date along with developing the organisation’s operational risk management framework as recommended by the recent external review. As part of the RMDP we are continuing to develop the linkages and escalation/de-escalation process with the Strategic Risk Register (SRR) and operational risk registers throughout the organisation. The Quality, Nursing and Allied Health Professionals Directorate (QNAHPs) is in the process of procuring further consultancy capacity to support this work and is continuing to pursue recruitment to the Head of Risk Management position.

# Corporate Risk Register

The CRR had been relatively unchanged for some time and LT has worked with the Risk Management Team to assess the status of each risk in the CRR, along with its actions and mitigations but also to capture potential new risks to be added to the register. Some of the risks were deemed to have happened and were moved to an issues log, and others were considered to have been addressed and were therefore archived.  Table 1 below shows the position for previous risks. The articulation, scoring, mitigation and actions for the current risks are not yet fully complete and will continue to be developed and addressed following this update as this live work on the CRR continues to be a priority business objective for the organisation.

In considering emerging corporate risks and those that can be archived/transferred to issues, LT has started to define risk escalation/de-escalation processes for the CRR and for operational level risks across the organisation. We acknowledge that these processes require strengthening and greater clarity, and this work will be completed as part of the RMDP.

Similarly, we will shortly commence work with the Planning and Performance Team and Health Protection to trial visualising the CRR and issues logs through a dashboard, acknowledging that the current spreadsheet presentation is difficult to use as a live tool.

The LT has considered the latest version of the CRR and identified the following:

  - Existing risks proposed to remain on the Corporate Risk Register

  - New risks identified to be added to the Corporate Risk Register

  - Risks proposed to be archived with explanation of why this decision has been made

  - Risks previously approved to be archived in August 2023 for completeness

An issues tab has been created alongside the Corporate Risk Register to be considered alongside corporate risks.

The full Corporate Risk Register is included in the table below:

Corporate Risk Register (November 2023)

| Risk | Lead Executive | Current Risk Score | Risk Decision |
| --- | --- | --- | --- |
| NEW: There is a risk that the organisation may not have the capacity or resources necessary to effectively deliver the long-term strategic plan. This risk arises from a challenging political and financial landscape, which includes staff time being redirected to contribute to the (Covid) public enquiry and an unstable industrial relations climate, which may strain existing resources, lead to burnout among the team, and hinder our ability to achieve the strategic objectives. | Director of People and Organisational Development​ | L3xI4 = 12​ | Treat​ |
| 207: There is a risk that Public Health Wales will fail to meet the requirements of The Health and Social Care (Quality and Engagement) (Wales) Act (2020), This will be caused by competing priorities, a lack of organisational capacity and capability to support timely implementation. The impact will be noncompliance with the legislative requirements, and a lack of progress in strengthening quality improvement and governance in the delivery of safe services, programmes and functions​ | Director for NHS Quality Improvement and Patient Safety, Improvement Cymru​ | L4xI4=16​ | Treat​ |
| 1531: There is a risk that we will fail to exploit data to inform and direct public health action and interventions caused by data being held in silos, difficulty accessing the data and inability to access to provide the impact on public health. resulting in worse public health outcomes in Wales and increased information governance risk within Public Health Wales​ | National Director of Data, Knowledge and Research ​ | L5xI4=20​ | Treat​ |
| 303: There is a risk that operational delivery of pathology services may be severely impacted if the new Laboratory Information Management System (LIMS) service is not fully deployed before the contract for the current LIMS expires in June 2025 resulting in potential delays in treatments, affecting the quality and safety of a broad spectrum of clinical services and the potential for financial and workforce impact.​ | Executive Director for Health Protection and Screening Services​ | L5xI4=20​ | Treat​ |

Table 1

Table 1 below shows the position for previous risks.

| Risk ID | Description | Directorate | Assessment November 2023 |
| --- | --- | --- | --- |
| 203 | DESW has insufficient capacity and is unable to meet the current and increasing demand for its service. | Health Protection and Screening Services (Screening) | Risk transferred to issues log: This has been on the CRR since 2018. To date the risk has not reduced from when first identified and it is proposed that it should be managed as an issue. A newly articulated risk will be added to the CRR that covers the whole of the DESW programme. |
| 207 | There is a risk that Public Health Wales will fail to meet the requirements of The Health and Social Care (Quality and Engagement) (Wales) Act (2020) | Quality, Nursing and Allied Health Professionals | This risk is proposed to be archived as the Duty of Candour implementation plan has been fully delivered with the exception of hosting and commissioning arrangements which now form part of business as usual within the Board Business Unit. New risk on Duty of Quality has been identified. |
| 206 | Risk that individual and team performance and development is not aligned with the organisation’s strategic and operational priorities | People and Organisational Development | Risk archived in August 2023: Job Planning, My Contribution, Workforce Planning and Education Commissioning processes should be considered and robust to manage this risk. |
| 301 | There is a risk that we will not deliver our IMTP (Integrated Medium Term Plan) due to challenges involved in securing resources at the right time, at the right cost, with the right skills | People and Organisational Development | Proposed to be archived: Actions being taken (as part of IMTP milestone 209) mitigate these risks and are being reported on monthly. |
| 208 | There is a risk that Health Protection and Screening Services will not be able to deliver high quality services in North Wales Infection division as they are struggling to recruit and retain sufficient medical and clinical staff. | Health Protection and Screening Services (Microbiology) | Risk transferred to issues log: This has been on the CRR since 2017. To date the risk has not reduced from when first identified and as such it is proposed that it should be managed as an issue. A new risk should be added to the CRR to articulate overall resource issues associated with HPSS rather than being specific to Microbiology. |
| 303 | There is a risk that the LINC process will not allow us to develop a product that meets our needs and is an improvement on the system currently in place. There is also a chance that the LINC programme will not be able to deliver and a Plan B will need to be put in place. This is a risk for both screening and microbiology. | Health Protection and Screening Services (Screening and Microbiology) | Risk has been re-articulated to cover operational delivery of pathology services. Discussions ongoing within Health Protection to potentially de-escalate to directorate level risk. |

# Management of issues in Public Health Wales

Public Health Wales has adopted the Enterprise Risk Management approach and as such the Risk Assurance Network has started to look at how the organisation manages issues.  The Institute of Risk Management defines an issue as “a risk that has happened, and therefore there is no uncertainty anymore.  Understanding issues is important to risk management as often these issues may have the potential to repeat, or trigger risks as a result of the issue occurring” (IRM, 2023).

This is included as a priority piece of work within the RMDP. LT is overseeing this work which will provide more guidance and training on how this can be operationalised locally and, and support Directorates to differentiate and manage issues, and in understand the relationship between risks and issues.

# Update on Risk Management Development Plan

An updated Risk Management Development Plan was approved in August 2023.  A further update on progress being made against the plan was discussed at LT on 2 November. The key highlights against each of the RMDP themes are as follows:

- Risk architecture: LT oversight of the CRR and operational risk management development has commenced. Promotion of Datix as the “single source of truth” started via Risk Management Network.

- Risk strategy: initial discussions held on risk appetite for CRR following the setting of strategic risk appetite by the Board.

- Risk protocols: strengthened use of Datix Web to record risks pending the delayed national implementation of Datix Cloud Risk Module (via Risk Management Network).

- Planning and design: early engagement with planning colleagues including risk management planning guidance for the IMTP re-fresh; two internal risk training modules nearing completion for roll-out in December.

- Risk implementation and benchmarking: forms part of external consultancy brief.

- Measuring and monitoring: forms part of external consultancy brief.

- Learning and development: visualisation of the CRR within the PAD, visualisation of operational and directorate level risks within the DADD; creation of issues log.

# Recommendation

The Board is asked to:

- Consider the latest version of the Corporate Risk Register

- Take Assurance that a robust process has been followed for agreeing which existing risks are to remain on the Corporate Risk Register; identifying new risks; and archiving old risks

- Take assurance on the progress being made on the Risk Management Development Plan.

- Take assurance on the management of Corporate Risks within the organisation.